Opportunity Sizing & Feasibility

Team 27 · Grand Prix Ticketing Redesign · Sprint 1, Week 2

Kartikey Dagar (Project Manager)  ·  Card T10  ·  4 hours

1. What this is

The opportunities carried out of the How Might We workshop, sized with both developers and judged against what we can realistically finish in the sprints we have left.

2. What we are sizing against

•  Firebase Spark plan — no Cloud Functions, no Cloud Storage, so no hosted images.

•  Vercel Hobby. No payment gateway.

•  Two sprints left after Sprint 1, roughly 60 hours each across five people.

•  No access to the client’s systems or real ticket data.

3. Sizing

C1 + C2 — the ticket explorer (browse, detail, compare)

What we would build: Three screens reading one Firestore collection — a list of ticket types, a detail view showing what each admits you to, and a side-by-side comparison of two or three.

Rough effort: 40–50 hours across the team, sized with Blake and Julius.

Deliverable in the time left? Yes. Fits inside one sprint with margin. Needs nothing we do not already have — Firestore, the auth that is already built, and sample data we seed ourselves.

C4 — help me choose (guided finder)

What we would build: A short set of questions — budget, days, priorities — ending in a recommended ticket type.

Rough effort: 15–20 hours.

Deliverable in the time left? Yes, but only once C1 exists — it recommends from the same data. Better as a Sprint 3 addition than a Sprint 2 feature.

C3 — what you would actually see

What we would build: A circuit map with zones, and a description of the view from each.

Rough effort: 20–25 hours, more if we chase real photography.

Deliverable in the time left? Partly. The value is visual, but hosted images need Cloud Storage on the paid plan. Text descriptions only would work and are cheap, but lose most of the point. Park it.

4. Recommendation

Take C1 + C2 into Sprint 2 as a single feature. It is the only option that is fully within our control, fits comfortably in one sprint, and can be demonstrated end to end to the client. C4 becomes the Sprint 3 addition if there is room, because it builds on the same data with no new infrastructure. C3 is parked — the version we could actually build on free tier is the weak version.

6. Risk register

| Risk | Likelihood / impact | Mitigation and owner |
| --- | --- | --- |
| Client never provides real ticket data | High / medium | Proceed on representative sample data — PM |
| No client sign-off on the chosen problem | Medium / high | Seek supervisor sign-off as fallback — PM |
| Free-tier limits block part of a feature | Low / high | Sized against Spark plan before committing — Dev 1 |
| Team availability during assessment periods | Medium / medium | Lighter scoping in peak weeks — PM |