## Plan
Plan ID | Plan name | Date of export
E8Zm73NkYkSyyv7o0ATFtcgAHZ1C | Week 4 - Project - Team 27 | 2026-08-16

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
hUAsDyswmEWzbu67imNF7MgAFkfc | Labels | Documents & Updates |  | Not started | Medium |  | Kartikey Anand Dagar | 2026-08-06 |  |  |  | false
PGfZrjWS-EihQXZTCApzGMgAMjHx | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | Done |  | Completed | Important | Kar Wei Kwong | Kartikey Anand Dagar | 2026-08-06 |  |  |  | false | 2026-08-16 | Kartikey Anand Dagar | 5/5 | Login scope explicitly stated as styling-only;Edge cases documented;Team page fields listed with validation/display rules;Document updated;Requirements shared with PM and UX | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on https://rmiteduau-my.sharepoint.com/:w:/g/personal/s4093980_student_rmit_edu_au/IQDo4gW23QEqSZ2ePi0sAXLLAfCeDdoKWuxaA4H-Nt9vxOo?e=NaFoXI
jlkEowUxg06NReYXxm38JcgAFKgb | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | Done |  | Completed | Medium |  | Kartikey Anand Dagar | 2026-08-06 |  |  |  | false | 2026-08-16 | Kartikey Anand Dagar | 0/5 | Login scope confirmed unchanged;Gaps (if any) sent back to UX and resolved;Document Updated;Design formally approved;Every required field checked against the design | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Document.docx
73Lx9yTpS0G1AKBisGb7NMgAM9K2 | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | Done |  | Completed | Medium |  | Kartikey Anand Dagar | 2026-08-06 |  |  |  | false | 2026-08-16 | Kartikey Anand Dagar | 4/4 | Visual style matches approved mockup;No authentication logic changed;Existing login validation/errors still function as before;Update document | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. update Document.docx
5csA5k3hjUCHSeOnBYwtTcgAAQao | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | Done |  | Completed | Medium |  | Kartikey Anand Dagar | 2026-08-06 |  |  |  | false | 2026-08-16 | Kartikey Anand Dagar | 4/4 | Successful login redirects to team page;Team page not directly accessible without login;Document updated;Team page renders per design with all required fields | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update Doc
pdqR-FvWiESKMaIZLkALpsgABTzI | [BOOTSTRAP RESTYLING] - Deploy - 120 | Done |  | Completed | Medium | Julius Ross | Kartikey Anand Dagar | 2026-08-06 |  |  |  | false | 2026-08-16 | Julius Ross | 4/4 | Live URL loads without errors;Document updated;Login → redirect → team page flow spot-checked on the deployed URL;Deployment completed via boilerplate pipeline | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc
iN6CzaiNWE-EPo6MvlOF38gACozH | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | Done |  | Completed | Medium |  | Kartikey Anand Dagar | 2026-08-06 |  |  |  | false | 2026-08-16 | Kartikey Anand Dagar | 4/4 | Document updated;Redirect to team page confirmed;Valid login tested end-to-end on deployed URL;All required content verified correct and complete | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document
Ht0Vl454SEqwEyFlnoFB3sgABu5f | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | Done |  | Completed | Medium | Julius Ross | Kartikey Anand Dagar | 2026-08-06 |  |  |  | false | 2026-08-16 | Kar Wei Kwong | 5/5 | Missing-photo and long-blurb edge cases tested;Invalid login tested;Bugs logged with repro steps, or none-found confirmed;Direct team-page access without login tested (must redirect);Update Document | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc
MkALNHQyQkOu52TLbqrMV8gANVCz | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | Done |  | Completed | Medium | Kartikey Anand Dagar | Kartikey Anand Dagar | 2026-08-06 |  |  |  | false | 2026-08-16 | Kartikey Anand Dagar | 3/3 | Feature reviewed end-to-end against requirements and design;All prior tasks' checklists verified complete;Task moved to Done | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off
dU2gsSWHb0CMqFDw8mNn0cgAE8m4 | [CLIENT MEETING SETUP] – Coordinate and schedule kickoff meeting with client: 60 | Done |  | Not started | Medium |  | Kartikey Anand Dagar | 2026-08-06 | 2026-08-07 |  |  | true |  |  | 1/1 | Discussing the best time for the meeting that works for both the team and the client

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
hUAsDyswmEWzbu67imNF7MgAFkfc | Labels | WCEnncq7IUS27i8bEIzUO8gAEhmm |  | Not started | Medium |  | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 |  |  |  | false
PGfZrjWS-EihQXZTCApzGMgAMjHx | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | E9coCl4Dfkizy5N8TBv3FcgAPM07 |  | Completed | Important | acd1c21f-02dc-4ad4-881a-393b294e6bc1 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 |  |  |  | false | 2026-08-16 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 5/5 | Login scope explicitly stated as styling-only;Edge cases documented;Team page fields listed with validation/display rules;Document updated;Requirements shared with PM and UX | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on https://rmiteduau-my.sharepoint.com/:w:/g/personal/s4093980_student_rmit_edu_au/IQDo4gW23QEqSZ2ePi0sAXLLAfCeDdoKWuxaA4H-Nt9vxOo?e=NaFoXI
jlkEowUxg06NReYXxm38JcgAFKgb | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | E9coCl4Dfkizy5N8TBv3FcgAPM07 |  | Completed | Medium |  | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 |  |  |  | false | 2026-08-16 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 0/5 | Login scope confirmed unchanged;Gaps (if any) sent back to UX and resolved;Document Updated;Design formally approved;Every required field checked against the design | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Document.docx
73Lx9yTpS0G1AKBisGb7NMgAM9K2 | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | E9coCl4Dfkizy5N8TBv3FcgAPM07 |  | Completed | Medium |  | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 |  |  |  | false | 2026-08-16 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 4/4 | Visual style matches approved mockup;No authentication logic changed;Existing login validation/errors still function as before;Update document | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. update Document.docx
5csA5k3hjUCHSeOnBYwtTcgAAQao | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | E9coCl4Dfkizy5N8TBv3FcgAPM07 |  | Completed | Medium |  | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 |  |  |  | false | 2026-08-16 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 4/4 | Successful login redirects to team page;Team page not directly accessible without login;Document updated;Team page renders per design with all required fields | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update Doc
pdqR-FvWiESKMaIZLkALpsgABTzI | [BOOTSTRAP RESTYLING] - Deploy - 120 | E9coCl4Dfkizy5N8TBv3FcgAPM07 |  | Completed | Medium | a218ceb2-d64a-44ed-8b12-2710a6a39207 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 |  |  |  | false | 2026-08-16 | a218ceb2-d64a-44ed-8b12-2710a6a39207 | 4/4 | Live URL loads without errors;Document updated;Login → redirect → team page flow spot-checked on the deployed URL;Deployment completed via boilerplate pipeline | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc
iN6CzaiNWE-EPo6MvlOF38gACozH | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | E9coCl4Dfkizy5N8TBv3FcgAPM07 |  | Completed | Medium |  | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 |  |  |  | false | 2026-08-16 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 4/4 | Document updated;Redirect to team page confirmed;Valid login tested end-to-end on deployed URL;All required content verified correct and complete | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document
Ht0Vl454SEqwEyFlnoFB3sgABu5f | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | E9coCl4Dfkizy5N8TBv3FcgAPM07 |  | Completed | Medium | a218ceb2-d64a-44ed-8b12-2710a6a39207 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 |  |  |  | false | 2026-08-16 | acd1c21f-02dc-4ad4-881a-393b294e6bc1 | 5/5 | Missing-photo and long-blurb edge cases tested;Invalid login tested;Bugs logged with repro steps, or none-found confirmed;Direct team-page access without login tested (must redirect);Update Document | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc
MkALNHQyQkOu52TLbqrMV8gANVCz | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | E9coCl4Dfkizy5N8TBv3FcgAPM07 |  | Completed | Medium | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 |  |  |  | false | 2026-08-16 | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 3/3 | Feature reviewed end-to-end against requirements and design;All prior tasks' checklists verified complete;Task moved to Done | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off
dU2gsSWHb0CMqFDw8mNn0cgAE8m4 | [CLIENT MEETING SETUP] – Coordinate and schedule kickoff meeting with client: 60 | E9coCl4Dfkizy5N8TBv3FcgAPM07 |  | Not started | Medium |  | 1bedc4ac-d429-42f6-83f6-b495d49e73a2 | 2026-08-06 | 2026-08-07 |  |  | true |  |  | 1/1 | Discussing the best time for the meeting that works for both the team and the client

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
utAtjYAOM0GTWZnQ4l7bdcgAFkeT | Blocked
WCEnncq7IUS27i8bEIzUO8gAEhmm | Documents & Updates
2_xTd81urEKllCjNldfVv8gALyzU | Backlog
Sn7qaxPeZ0WdHkC2F1WOwMgAHQpR | Doing
r6BEuJ7x6k68NPb0nYQgZ8gAKLQV | Reviewing
E9coCl4Dfkizy5N8TBv3FcgAPM07 | Done
nRMvPUBfc0iBzbReW7lb2MgAKFVn | Testing
FLuLjuKmSUKdxAJeD8NAScgAH6T7 | Done
Vb5F0D5fIUiccxs_kU5UyMgAEgSN | Clean up

## Users
User ID | User Name | Email
1bedc4ac-d429-42f6-83f6-b495d49e73a2 | Kartikey Anand Dagar | S4037651@student.rmit.edu.au
acd1c21f-02dc-4ad4-881a-393b294e6bc1 | Kar Wei Kwong | S4093980@student.rmit.edu.au
a218ceb2-d64a-44ed-8b12-2710a6a39207 | Julius Ross | S4016992@student.rmit.edu.au