## Summary
S3W2 - Regression suite and production content audit
Grand Prix ticket explorer - Team 27, Capstone 2026. Sources: Sprint 2 user stories and acceptance criteria, S3W1 accessibility and error-handling criteria, Sprint 2 defects G-01 to G-16, and the Production Content Standard (CS-01 to CS-16). Run on the deployed site on 18 Oct 2026 in the Claude desktop app's built-in browser, signed in, at about 800px and 375px widths. Re-checked on the new front end the same evening.
Regression by area | Pass | Fail | Blocked | Not built | Not tested | Total
Entry and navigation | 4 | 0 | 0 | 0 | 0 | 4
Browse | 4 | 1 | 0 | 3 | 0 | 8
Detail | 3 | 2 | 1 | 2 | 0 | 8
Selection limits | 7 | 0 | 0 | 1 | 0 | 8
Compare | 4 | 1 | 0 | 1 | 0 | 6
Fallback states | 1 | 0 | 6 | 0 | 0 | 7
Firestore read failures | 2 | 2 | 2 | 2 | 0 | 8
Accessibility smoke | 4 | 0 | 0 | 0 | 0 | 4
Total | 29 | 6 | 9 | 9 | 0 | 53
Pass rate (of scenarios run) | [5 empty] | 54.72%
Content audit and links | Pass | Fail | N/A | Not tested |  | Total
Content audit checks | 28 | 23 | 0 | 4 |  | 55
Links (Yes = resolves) | 13 | 3 | 6 |  |  | 22
Gaps by severity | Critical | High | Medium | Low | Open | Total
Gap List | 0 | 4 | 10 | 13 | 19 | 27
How to use
Yellow cells are for you to fill in. Run everything on the deployed site, at desktop (1440px) and mobile (375px) widths.
1. Regression Scenarios (53): run each one, write the Actual result and pick a Result. P1 scenarios first; they are the smoke test for every release.
2. Content Audit (55 checks): check each screen against the Production Content Standard rule shown. N/A if the screen doesn't have that content.
3. Link Check: click every link and navigating button, record where it goes and whether it resolves. Replace [bracketed] rows with the real links.
4. Gap List: log every Fail and every link that doesn't resolve, with a severity, then put the Gap ID back on the row that found it.
5. Hand the Gap List to both developers with severities (last checklist item).
Selection limit and Compare scenarios assume Compare takes 2-3 tickets (S3W1 Q-02, still to confirm). Adjust Then if the team decides otherwise.
Severity: Critical = blocks the journey or shows wrong info; High = breaks a rule users notice; Medium = inconsistent but usable; Low = cosmetic.

## Regression Scenarios
ID | Area | Priority | Source (AC / S3W1 / defect / CS) | Scenario | Given | When | Then (expected) | Actual result | Result | Gap ID | Date tested | Notes
ENTRY AND NAVIGATION
RS-01 | Entry and navigation | P1 | S1 AC | Reach the ticket explorer | User is signed in on the Dashboard | User selects "Browse tickets" | Browse page opens and lists ticket types; URL is /tickets | Dashboard "Browse tickets" opens /tickets with all 6 ticket types | Pass |  | 18/10/2026
RS-02 | Entry and navigation | P1 | S1 AC | Direct link to Browse | User is signed in | User opens /tickets directly or refreshes it | Browse loads the same as from the Dashboard | Opening /tickets directly loads Browse; signed-out users are sent to sign-in and back | Pass |  | 18/10/2026
RS-03 | Entry and navigation | P2 | CS-14 | Page titles | User moves between Dashboard, Browse and Compare | User checks the browser tab title | Each page has its own title, e.g. "Tickets - [site name]" | App pages titled "Dashboard ¦ Grand Prix Ticketing", "Browse tickets ¦ ...", "Compare tickets ¦ ..." | Pass |  | 18/10/2026 | Public home page title is just "Home" (S3-02)
RS-04 | Entry and navigation | P2 | S2 Q-10 | Browser back from Browse | User came from the Dashboard to Browse | User presses the browser back button | User returns to the Dashboard with no error | Browser back from Browse returns to the Dashboard | Pass |  | 18/10/2026
BROWSE
RS-05 | Browse | P1 | S1 AC | All ticket types on one screen | Ticket data loads | User opens Browse | Every ticket type shows as a card; none are missing or duplicated | 6 ticket types shown as cards, no duplicates | Pass |  | 18/10/2026
RS-06 | Browse | P1 | S1 AC / CS-01 / CS-02 | Card content | Ticket data loads | User reads any card | Card shows tier name, price, zone, view quality and days covered, formatted per CS-01 and CS-02 | Name, price, zone and days shown; no tier badge or view quality indicator; days shown as day names | Fail | S3-04 | 18/10/2026 | Also S3-03 (dates). Sprint 2 G-01 and G-09 still open
RS-07 | Browse | P1 | S1 AC / G-02 | Ticket order | Several ticket types with different prices | User opens Browse | Cards follow the agreed recommended order, with price ascending as tie-breaker | Sorted by price ascending: $235, $545, $620, $890, $1,150, $4,950 | Pass |  | 18/10/2026 | Sprint 2 G-02 fixed
RS-08 | Browse | P2 | S1 AC / CS-07 | Sold-out card | One ticket type has 0 left | User views that card | "Sold out" label shows, button is disabled, card is muted but readable | No stock data; sold-out state can't occur | Not built | S3-07 | 18/10/2026 | G-04 still open
RS-09 | Browse | P2 | S1 AC / CS-07 | Low-stock label | One ticket type has fewer than 20 left | User views that card | "Only X left" shows with the right number; button stays enabled | No stock data; low-stock label can't occur | Not built | S3-07 | 18/10/2026
RS-10 | Browse | P2 | S1 AC / G-05 | Price range | One ticket type has more than one price | User views that card | Card shows a range, e.g. "$450-$550" | One price per ticket type; ranges not supported | Not built | S3-08 | 18/10/2026 | G-05 still open
RS-11 | Browse | P2 | S1 Responsive | Mobile layout | Screen is 375px wide | User opens Browse | Cards stack in one column; no text cut off; no sideways scrolling | At 375px cards stack in one column; no sideways scroll; no text under 12px; all buttons at least 44px | Pass |  | 18/10/2026 | Sprint 2 G-08 (button size) fixed
RS-12 | Browse | P3 | S1 Interactions / G-03 | Hover and pressed states | Desktop browser | User hovers a card, then clicks and holds a button | Card shows a hover state; button shows a pressed state | Pressing and holding a button doesn't change its look (no pressed/active state) | Pass |  | 18/10/2026 | Tested by Matthew in Chrome, new front end. Sprint 2 G-03 (active state) still open. Accepted as a pass by the BA: difference is marginal
DETAIL
RS-13 | Detail | P1 | S2 AC | Open the right ticket | Browse is loaded | User selects "View details" on the Grandstand card | Detail opens for Grandstand with the same price, days and zone as its card | "View details" on Turn 11 opens a modal with matching name, price, days and zone; URL updates to ?ticket=... | Pass |  | 18/10/2026
RS-14 | Detail | P1 | S2 AC / G-09 / CS-03 | Real dates | Detail is open for a multi-day ticket | User reads the dates | Actual dates show, e.g. "Fri 13 - Sun 15 Mar 2026", not just day names | Shows "Sat, Sun" / "Thu, Fri, Sat, Sun", not real dates | Fail | S3-03 | 18/10/2026 | G-09 still open
RS-15 | Detail | P1 | S2 AC / G-10 / CS-04 | Zone, seat description and map | Detail is open | User reads the zone section | Zone name, a seat description and the zone map (with alt text) all show | New front end: zone, map and description shown; every ticket still says "Seat allocation not specified for this ticket." | Fail | S3-05 | 18/10/2026
RS-16 | Detail | P2 | S2 AC / CS-06 | Includes and excludes | Detail is open | User reads both lists | Both lists show, written per CS-06; empty Excludes reads "Not specified for this ticket" | "What's included" and "What's not included" lists shown, parallel noun-first items | Pass |  | 18/10/2026
RS-17 | Detail | P2 | S2 Edge / G-13 / CS-16 | Restriction callout | Ticket has a restriction such as 18+ | User opens Detail | Restriction shows in a visible callout | No ticket in the catalogue has a restriction to check | Blocked |  | 18/10/2026 | Needs a test ticket with a restriction (G-13)
RS-18 | Detail | P1 | S2 Interactions / G-11 | Add to cart | Cart is empty | User selects "Add to cart" | Cart count goes from 0 to 1 and a confirmation appears | No Add to cart; button is "Add to selection"; /cart and /checkout return 404 | Not built | S3-06 | 18/10/2026 | G-11 still open
RS-19 | Detail | P2 | S2 Q-07 | Add the same ticket twice | Ticket is already in the cart | User selects "Add to cart" again | Quantity goes up by 1; no duplicate line | No cart, so can't add twice | Not built | S3-06 | 18/10/2026
RS-20 | Detail | P2 | S2 Interactions | Close keeps position | User scrolled down Browse, then opened Detail | User closes Detail with X or Esc | Browse shows at the same scroll position; focus returns to the "View details" button | Esc closes the modal and focus returns to the "View details" button; focus stays inside the modal while open | Pass |  | 18/10/2026
SELECTION LIMITS
RS-21 | Selection limits | P1 | Compare (Q-02) | Select tickets to compare | Browse is loaded | User selects 2 tickets for comparison | Both show as selected and a "Compare tickets" action becomes available | New front end: ticking "Compare" on 2 cards shows "2 ticket types selected" and a Compare link | Pass |  | 18/10/2026 | Selection is now a Compare checkbox on each card
RS-22 | Selection limits | P1 | Compare (Q-02) | Maximum selection | 3 tickets are already selected | User tries to select a 4th | The 4th isn't added and a message says "You can compare up to 3 tickets" | At 3, the other Compare checkboxes are disabled; text says "Remove one to select another." | Pass |  | 18/10/2026
RS-23 | Selection limits | P1 | Compare (Q-02) / EMP-05 | Minimum selection | Only 1 ticket is selected | User tries to compare | Compare isn't available, or shows "Add at least one more ticket to compare" | With 1 selected there is no Compare link; Compare page says "You need to select at least two ticket types before comparing." | Pass |  | 18/10/2026
RS-24 | Selection limits | P2 | Compare (Q-02) | Deselect a ticket | 2 tickets are selected | User deselects one | Selection count drops to 1 and the compare action updates | Remove drops the count and updates the compare link | Pass |  | 18/10/2026
RS-25 | Selection limits | P2 | Compare (Q-02) | Same ticket twice | A ticket is already selected | User selects it again | It isn't added twice; selecting again removes it or does nothing | Selecting the same ticket again removes it (toggle) | Pass |  | 18/10/2026
RS-26 | Selection limits | P2 | Compare (Q-02) | Sold-out tickets | One ticket type is sold out | User tries to select it for comparison | Behaviour matches the agreed rule (can compare but not buy, or can't select) and is clearly labelled | No stock data, so no sold-out tickets to try | Not built | S3-07 | 18/10/2026
RS-27 | Selection limits | P2 | Compare (Q-02) | Selection survives navigation | 2 tickets are selected | User opens Detail for another ticket, then closes it | The 2 tickets are still selected | Selection kept when going Browse -> Compare, but lost on page refresh | Pass | S3-13 | 18/10/2026 | Refresh loss logged as Low
RS-28 | Selection limits | P3 | Compare (Q-02) | Clear all | 3 tickets are selected | User selects "Clear all" | All selections are removed | "Clear selection" resets to 0 selected | Pass |  | 18/10/2026
COMPARE
RS-29 | Compare | P1 | Compare (Q-02) | Side-by-side comparison | 2 or 3 tickets are selected | User opens Compare | Selected tickets show side by side with the same rows for each | 3 tickets shown side by side in a table: map, price, days, zone, view, includes, excludes; differing rows highlighted | Pass |  | 18/10/2026
RS-30 | Compare | P1 | Compare / CS-01 to CS-03 | Values match other screens | Compare is open | User checks price, dates and zone against Browse and Detail | All values match exactly | Prices, days and zones match Browse and Detail exactly | Pass |  | 18/10/2026
RS-31 | Compare | P2 | Compare | Remove from Compare | 3 tickets are compared | User removes one | It disappears and the other 2 stay; focus moves sensibly | New front end: Remove works, but focus still drops to the page body | Fail | S3-14 | 18/10/2026
RS-32 | Compare | P2 | EMP-04 | Compare with nothing selected | No tickets are selected | User opens Compare | "Select 2 or 3 tickets to compare" shows with a "Browse tickets" link | Shows "Select at least two tickets to compare..." with a "Browse tickets" link | Pass |  | 18/10/2026 | Wording differs slightly from EMP-04 but meets the intent
RS-33 | Compare | P2 | Compare / S1 Responsive | Compare on mobile | Screen is 375px wide | User opens Compare with 3 tickets | Content stacks or scrolls within its own area; no page-wide sideways scrolling | At phone width with 3 tickets, Compare shows but the page has a little sideways play when scrolled left | Pass |  | 18/10/2026 | Tested by Matthew in Chrome device mode. Swiping right triggers the browser's back gesture, which is expected. Accepted as a pass by the BA: difference is marginal
RS-34 | Compare | P2 | Compare | Add to cart from Compare | Compare is open | User adds one ticket to the cart | That ticket is added, the cart count updates, and Compare stays open | No Add to cart on Compare | Not built | S3-06 | 18/10/2026
FALLBACK STATES
RS-35 | Fallback states | P1 | S1 Empty / G-07 | Loading state | Network is throttled to Slow 3G | User opens Browse | Skeleton cards show, then real cards replace them | New front end: dark skeleton cards show while tickets load on 3G, then real cards replace them | Pass |  | 18/10/2026 | Re-tested by Matthew in Chrome on the new front end. Old version showed a spinner (S3-18, now closed)
RS-36 | Fallback states | P2 | EMP-01 / G-06 | All sold out | Every ticket type is sold out | User opens Browse | "All tickets are currently sold out. Check back later." shows with a waitlist link | Can't make tickets sold out (no stock data) | Blocked |  | 18/10/2026 | Depends on G-04
RS-37 | Fallback states | P2 | EMP-02 | No ticket types | No ticket types exist | User opens Browse | "No tickets are on sale yet. Check back soon." shows; no empty cards |  | Blocked |  | 18/10/2026 | Needs an empty ticket catalogue on a test environment
RS-38 | Fallback states | P2 | FS-05 / CS-05 | Missing view description | A ticket has no view description | User opens its Detail | "View description coming soon" shows |  | Blocked |  | 18/10/2026 | All tickets have descriptions; needs test data
RS-39 | Fallback states | P2 | FS-04 | Missing zone map | A ticket has no zone map | User opens its Detail | "Zone map not available" shows and the seat description is still there |  | Blocked |  | 18/10/2026 | All tickets have maps; needs test data
RS-40 | Fallback states | P2 | FS-06 / CS-11 | Missing required field | A ticket has no name or no price | User opens Browse and Compare | That ticket is hidden; no "undefined", "NaN" or "$0" shows |  | Blocked |  | 18/10/2026 | Needs a test ticket missing name or price
RS-41 | Fallback states | P3 | CS-13 | Broken image | A ticket image URL is wrong | User opens Browse | A fallback image or neutral placeholder shows, not a broken image icon |  | Blocked |  | 18/10/2026 | Needs a ticket with a broken image URL
FIRESTORE READ FAILURES
RS-42 | Firestore read failures | P1 | FS-01 | Permission denied | Firestore rules deny access | User opens Browse | A friendly message with Retry shows; "Missing or insufficient permissions" never shows |  | Blocked |  | 18/10/2026 | A developer needs to deny Firestore access on a test deploy (Tickets are read in the browser from Firestore via documents:runQuery.)
RS-43 | Firestore read failures | P1 | ERR-01 / G-14 | Load failure | The ticket request fails (offline in dev tools) | User opens Browse | "We couldn't load tickets right now. Please try again." shows with Retry; no raw API error | Blocked firestore.googleapis.com in DevTools and reloaded /tickets: page shows only a loading spinner indefinitely; no message, no Retry | Fail | S3-25 | 18/10/2026 | Tested by Matthew in Chrome (Network request blocking), new front end
RS-44 | Firestore read failures | P1 | ERR-02 | Retry recovers | The load failed and the connection is back | User selects Retry | Tickets load and the error disappears | No Retry button exists, so the user can only reload the page | Not built | S3-25 | 18/10/2026
RS-45 | Firestore read failures | P2 | ERR-03 | Retry fails again | The connection is still down | User selects Retry | Same message stays; Retry still works; no reload loop | No Retry button exists | Not built | S3-25 | 18/10/2026
RS-46 | Firestore read failures | P2 | FS-02 | Slow response | Firestore takes more than 10 seconds | User opens Browse | Loading is replaced by the error message with Retry | With Firestore blocked the request never succeeds and the spinner never times out, so the 10-second rule (FS-02) isn't met | Fail | S3-25 | 18/10/2026 | Tested via request blocking rather than a slow response
RS-47 | Firestore read failures | P2 | FS-03 | Offline after load | Browse has loaded, then the device goes offline | User opens a Detail that needs new data | "You're offline. Check your connection and try again." shows; existing content stays | Loaded /tickets online, then went offline: tickets stay on screen with no errors | Pass |  | 18/10/2026 | Tested by Matthew in Chrome, 18/10
RS-48 | Firestore read failures | P2 | ERR-04 | Detail load failure | The Detail request fails | User opens Detail | Modal shows "We couldn't load this ticket. Please try again." with Retry and Close | Offline after load, ticket details still open with full data and no errors (data already on the page) | Pass |  | 18/10/2026 | Tested by Matthew in Chrome, 18/10. A true load failure is covered by RS-43 with request blocking
RS-49 | Firestore read failures | P2 | ERR-08 | Partial failure in Compare | One of 3 compared tickets fails to load | User opens Compare | The other 2 show; the failed one shows "Couldn't load this ticket" with Retry |  | Blocked |  | 18/10/2026 | Needs a developer to make one ticket fail on a test deploy (Tickets are read in the browser from Firestore via documents:runQuery.)
ACCESSIBILITY SMOKE
RS-50 | Accessibility smoke | P1 | A11Y-07 / A11Y-08 | Keyboard journey | Mouse is not used | User tabs from Browse to Detail to Compare and back | Every control is reachable in reading order; focus enters and leaves the modal correctly | Modal: focus moves in, stays trapped, returns on Esc. Compare: removing a ticket loses focus | Pass |  | 18/10/2026 | Full page tab-through not done; Compare focus issue logged as S3-14
RS-51 | Accessibility smoke | P1 | A11Y-09 | Visible focus | User is tabbing | User looks at the focused element | A clear outline shows on every focused element | 2px solid focus outline on focused controls | Pass |  | 18/10/2026
RS-52 | Accessibility smoke | P2 | A11Y-04 / A11Y-05 | Contrast | Lighthouse is run on each screen | User checks the accessibility audit | No contrast failures, including muted sold-out cards | New front end: lowest text contrast is the red price at 4.0:1 on 24px bold, which meets the 3:1 large-text rule; body text 13.5:1 | Pass |  | 18/10/2026 | S3-15 closed
RS-53 | Accessibility smoke | P2 | A11Y-10 / A11Y-12 | Screen reader names and messages | VoiceOver is on | User goes through Browse, Detail and Compare | Every button has a clear name; added-to-cart, error and limit messages are announced | New front end: Compare checkboxes are labelled "Compare <ticket name>"; buttons have clear names | Pass |  | 18/10/2026 | S3-16 closed. VoiceOver not run

## Content Audit
ID | Screen | Rule | Rule name | Passes when | What I saw | Result | Gap ID | Notes
DASHBOARD
CA-01 | Dashboard | CS-08 | Button labels | Verb first, sentence case, same label for same action | Mobile bottom nav calls the Dashboard "Home"; sidebar calls it "Dashboard" | Fail | S3-23
CA-02 | Dashboard | CS-10 | Spelling, grammar and case | Australian English, no typos, sentence case | No spelling issues found | Pass
CA-03 | Dashboard | CS-11 | No placeholder or test content | No lorem ipsum, TBD, test, undefined, null, NaN | Ticket pass shows "Your Name", "QR", "Row 1 · Seat 1" | Fail | S3-10
CA-04 | Dashboard | CS-12 | Brand | Grand Prix palette (red, black, white) and typography | Colours now Grand Prix red and black (S3-17 closed), but the logo says "GARAGE", the template name | Fail | S3-21
CA-05 | Dashboard | CS-13 | Images | No broken images; meaningful images have alt text |  | Not tested
CA-06 | Dashboard | CS-14 | Page titles and headings | Unique page title; one main heading | "Dashboard ¦ Grand Prix Ticketing" | Pass
CA-07 | Dashboard | CS-15 | Links | Descriptive text; resolves; goes where it says (see Link Check) | 10 links go to "#" and do nothing | Fail | S3-09
BROWSE
CA-08 | Browse | CS-01 | Ticket names | Official tier name, Title Case, 40 chars or fewer, same on every screen | Same 6 names on Browse, Detail and Compare | Pass
CA-09 | Browse | CS-02 | Prices | $ sign, whole dollars, ranges with a dash; never $0 or NaN | "$235 AUD" ... "$4,950 AUD" | Pass
CA-10 | Browse | CS-03 | Dates | Real dates with day names, e.g. Fri 13 - Sun 15 Mar 2026 | Day names only: "Thu, Fri, Sat, Sun" | Fail | S3-03
CA-11 | Browse | CS-07 | Stock labels | Exactly "Sold out" / "Only X left", shown as text | No stock labels exist | Fail | S3-07
CA-12 | Browse | CS-08 | Button labels | Verb first, sentence case, same label for same action | "View details", "Add to selection", "Highlight zone", "Clear selection" | Pass
CA-13 | Browse | CS-09 | Error, empty and fallback messages | Match S3W1 ERR/EMP/FS wording; no technical text |  | Not tested
CA-14 | Browse | CS-10 | Spelling, grammar and case | Australian English, no typos, sentence case | Ticket names, buttons and headings shown in ALL CAPS | Fail | S3-24
CA-15 | Browse | CS-11 | No placeholder or test content | No lorem ipsum, TBD, test, undefined, null, NaN | Tickets page now also shows the "Your Name" / "Row 1 · Seat 1" pass | Fail | S3-10
CA-16 | Browse | CS-12 | Brand | Grand Prix palette (red, black, white) and typography | Colours now Grand Prix red and black (S3-17 closed), but the logo says "GARAGE", the template name | Fail | S3-21
CA-17 | Browse | CS-13 | Images | No broken images; meaningful images have alt text | Each card map is labelled with its zone | Pass
CA-18 | Browse | CS-14 | Page titles and headings | Unique page title; one main heading | "Browse tickets ¦ Grand Prix Ticketing", one h1 | Pass
CA-19 | Browse | CS-15 | Links | Descriptive text; resolves; goes where it says (see Link Check) | Tickets page now also has 8 links to "#" (upgrades and events) | Fail | S3-09
DETAIL
CA-20 | Detail | CS-01 | Ticket names | Official tier name, Title Case, 40 chars or fewer, same on every screen | Matches card | Pass
CA-21 | Detail | CS-02 | Prices | $ sign, whole dollars, ranges with a dash; never $0 or NaN | Matches card | Pass
CA-22 | Detail | CS-03 | Dates | Real dates with day names, e.g. Fri 13 - Sun 15 Mar 2026 | Day names only | Fail | S3-03
CA-23 | Detail | CS-04 | Zone and seat | Zone name plus a 1-2 sentence seat description | "Seat allocation not specified for this ticket." on every ticket | Fail | S3-05
CA-24 | Detail | CS-05 | View description | Plain language, 15-60 words; else "View description coming soon" | Plain one-sentence view descriptions | Pass
CA-25 | Detail | CS-06 | Includes and excludes | Parallel noun-first items, sentence case, no full stops | Parallel noun-first items, no full stops | Pass
CA-26 | Detail | CS-07 | Stock labels | Exactly "Sold out" / "Only X left", shown as text | No stock labels exist | Fail | S3-07
CA-27 | Detail | CS-08 | Button labels | Verb first, sentence case, same label for same action | "Add to selection" (no Add to cart) | Fail | S3-06
CA-28 | Detail | CS-09 | Error, empty and fallback messages | Match S3W1 ERR/EMP/FS wording; no technical text | "Ticket not found" message is plain with a next step | Pass
CA-29 | Detail | CS-10 | Spelling, grammar and case | Australian English, no typos, sentence case | Ticket names, buttons and headings shown in ALL CAPS | Fail | S3-24
CA-30 | Detail | CS-11 | No placeholder or test content | No lorem ipsum, TBD, test, undefined, null, NaN | No placeholder text | Pass
CA-31 | Detail | CS-12 | Brand | Grand Prix palette (red, black, white) and typography | Colours now Grand Prix red and black (S3-17 closed), but the logo says "GARAGE", the template name | Fail | S3-21
CA-32 | Detail | CS-13 | Images | No broken images; meaningful images have alt text | Map alt "Albert Park Grand Prix Circuit map" | Pass
CA-33 | Detail | CS-15 | Links | Descriptive text; resolves; goes where it says (see Link Check) | "Back to browse" resolves | Pass
CA-34 | Detail | CS-16 | Restrictions and conditions | Age limits etc. in a visible callout | No ticket has a restriction to check | Not tested
COMPARE
CA-35 | Compare | CS-01 | Ticket names | Official tier name, Title Case, 40 chars or fewer, same on every screen | Matches Browse | Pass
CA-36 | Compare | CS-02 | Prices | $ sign, whole dollars, ranges with a dash; never $0 or NaN | "$235", "$620", "$1,150" | Pass
CA-37 | Compare | CS-03 | Dates | Real dates with day names, e.g. Fri 13 - Sun 15 Mar 2026 | Day names only | Fail | S3-03
CA-38 | Compare | CS-04 | Zone and seat | Zone name plus a 1-2 sentence seat description | Zone and approximate area only; no seat description | Fail | S3-05
CA-39 | Compare | CS-05 | View description | Plain language, 15-60 words; else "View description coming soon" | Matches Detail | Pass
CA-40 | Compare | CS-06 | Includes and excludes | Parallel noun-first items, sentence case, no full stops | Matches Detail | Pass
CA-41 | Compare | CS-07 | Stock labels | Exactly "Sold out" / "Only X left", shown as text | No stock labels exist | Fail | S3-07
CA-42 | Compare | CS-08 | Button labels | Verb first, sentence case, same label for same action | "Remove", "Highlight zone", "Back to tickets" | Pass
CA-43 | Compare | CS-09 | Error, empty and fallback messages | Match S3W1 ERR/EMP/FS wording; no technical text | Minimum-selection message is plain with a link | Pass
CA-44 | Compare | CS-10 | Spelling, grammar and case | Australian English, no typos, sentence case | Ticket names, buttons and headings shown in ALL CAPS | Fail | S3-24
CA-45 | Compare | CS-11 | No placeholder or test content | No lorem ipsum, TBD, test, undefined, null, NaN | No placeholder text | Pass
CA-46 | Compare | CS-12 | Brand | Grand Prix palette (red, black, white) and typography | Colours now Grand Prix red and black (S3-17 closed), but the logo says "GARAGE", the template name | Fail | S3-21
CA-47 | Compare | CS-13 | Images | No broken images; meaningful images have alt text | Maps labelled per zone | Pass
CA-48 | Compare | CS-14 | Page titles and headings | Unique page title; one main heading | "Compare tickets ¦ Grand Prix Ticketing", one h1 | Pass
CA-49 | Compare | CS-15 | Links | Descriptive text; resolves; goes where it says (see Link Check) | "Back to tickets" and "Browse tickets" resolve | Pass
CA-50 | Compare | CS-16 | Restrictions and conditions | Age limits etc. in a visible callout | No ticket has a restriction to check | Not tested
ERROR AND EMPTY STATES
CA-51 | Error and empty states | CS-09 | Error, empty and fallback messages | Match S3W1 ERR/EMP/FS wording; no technical text | Not found and empty Compare messages are plain; load errors not triggered | Pass
CA-52 | Error and empty states | CS-10 | Spelling, grammar and case | Australian English, no typos, sentence case | No issues found | Pass
CA-53 | Error and empty states | CS-11 | No placeholder or test content | No lorem ipsum, TBD, test, undefined, null, NaN | Settings page says "Settings will appear here."; auth pages' meta description is "Built on garage-boilerplate" | Fail | S3-12
CA-54 | Error and empty states | CS-12 | Brand | Grand Prix palette (red, black, white) and typography | Colours now Grand Prix red and black (S3-17 closed), but the logo says "GARAGE", the template name | Fail | S3-21
CA-55 | Error and empty states | CS-15 | Links | Descriptive text; resolves; goes where it says (see Link Check) | "Back to browse" and "Browse tickets" resolve | Pass

## Link Check
ID | Screen | Link or button text | Expected destination | Actual destination | Resolves? | Gap ID | Notes
LC-01 | Dashboard | Browse tickets | /tickets (Browse) | /tickets | Yes
LC-02 | Dashboard | [each other Dashboard link] | [its page] | Full standings, View full calendar, View all upgrades, 3 Upgrade links, 4 event links all go to "#" | No | S3-09 | 10 dead links
LC-03 | Header / nav | [each header link, e.g. logo, Home] | [its page] | Dashboard, Tickets, Team, Profile, Settings all load; Sign out button present | Yes
LC-04 | Browse | View details (each of the 6 ticket types) | Detail for that ticket | Opens the right ticket in a modal (?ticket=...) | Yes |  | All 6 checked
LC-05 | Browse | Compare tickets | Compare with the selected tickets | /tickets/compare with the selected tickets | Yes
LC-06 | Browse | Join the waitlist (sold-out empty state) | Waitlist / availability notification page | No sold-out state, so no waitlist link | N/A |  | Depends on G-04
LC-07 | Browse | Clear filters (no-results state) | Full ticket list | No filters on Browse | N/A
LC-08 | Browse | Retry (error state) | Reloads tickets on the same page |  |  |  | Not tested: needs offline mode
LC-09 | Detail | Close (X) | Back to Browse, same scroll position | Closes modal, back to Browse | Yes
LC-10 | Detail | Add to cart | Adds to cart; cart count updates | No Add to cart; /cart returns 404 | No | S3-06
LC-11 | Detail | Back to tickets (ticket not found) | /tickets (Browse) | "Back to browse" returns to /tickets | Yes |  | Label is "Back to browse"
LC-12 | Detail | [any other link in the modal] | [its page] | No other links in the modal | N/A
LC-13 | Compare | Browse tickets (nothing selected) | /tickets (Browse) | /tickets | Yes
LC-14 | Compare | Remove (each ticket) | Removes that ticket, stays on Compare | Removes the ticket, stays on Compare | Yes
LC-15 | Compare | View details (each ticket) | Detail for that ticket | No View details on Compare | N/A
LC-16 | Compare | Add to cart (each ticket) | Adds to cart; cart count updates | No Add to cart on Compare | No | S3-06
LC-17 | Footer | [each footer link, e.g. Terms, Privacy, FAQ, Contact] | [its page] | No footer on app pages | N/A
LC-18 | Cart | Cart icon / link | Cart or checkout page | No cart icon | N/A
LC-19 | Home | Sign in | /auth/signin | /auth/signin | Yes
LC-20 | Home | Get your tickets | /auth/signup | /auth/signup | Yes
LC-21 | Browse | Back to dashboard | /dashboard | /dashboard | Yes
LC-22 | Compare | Back to tickets | /tickets | /tickets | Yes
LC-23 | Header | Profile icon | /profile | /profile | Yes
LC-24
LC-25
LC-26
LC-27
LC-28
Rows in [brackets] are placeholders: add one row per real link you find on that screen.

## Gap List
Gap ID | Title | Found in (RS / CA / LC ID) | Screen | Steps to reproduce | Expected | Actual | Severity | Screenshot link | Assigned to | Status | Date logged
S3-00 (example) | Waitlist link returns 404 | LC-06, CA-15 | Browse | 1. Make every ticket type sold out 2. Open /tickets 3. Select "Join the waitlist" | Waitlist page opens | 404 page | High | (paste link) | (developer) | Open | 17/10/2026
S3-01 | Leftover template text in meta description | CA (Error and empty states, CS-11) | Sign in / Sign up | 1. Open /auth/signin 2. View page source or a link preview | A real description of the site | "Built on garage-boilerplate" | Low |  |  | Open | 18/10/2026
S3-02 | Home page title is just "Home" | RS-03 | Home | 1. Open the home page 2. Read the browser tab | "Home ¦ Grand Prix Ticketing" | "Home" | Low |  |  | Open | 18/10/2026
S3-03 | Day names shown instead of real dates | RS-06, RS-14, CA CS-03 | Browse, Detail, Compare | 1. Open /tickets 2. Read "Days covered" on any 4-day ticket | Real dates: day, date and month | "Thu, Fri, Sat, Sun" (Sprint 2 G-09 still open) | Medium |  |  | Open | 18/10/2026
S3-04 | No tier badge or view quality indicator on cards | RS-06 | Browse | 1. Open /tickets 2. Look at any card | Tier badge/label and a view quality indicator | Neither shown (Sprint 2 G-01 still open) | Medium |  |  | Open | 18/10/2026
S3-05 | No seat description on any ticket | RS-15, CA CS-04 | Detail, Compare | 1. Open details for any ticket 2. Read "Zone and location" | 1-2 sentence seat description | "Seat allocation not specified for this ticket." on all 6 | Medium |  |  | Open | 18/10/2026
S3-06 | No cart: no Add to cart, /cart is 404 | RS-18, RS-19, RS-34, LC-10, LC-16 | Detail, Compare | 1. Open any ticket's details 2. Look for Add to cart 3. Open /cart | Add to cart updates a cart count | Only "Add to selection"; /cart and /checkout return 404 (Sprint 2 G-11 still open) | High |  |  | Open | 18/10/2026
S3-07 | Stock and availability not built | RS-08, RS-09, RS-26, RS-36, CA CS-07 | Browse, Detail, Compare | 1. Open /tickets 2. Look for sold-out or low-stock labels | "Sold out" and "Only X left" states | No stock data, so these states never appear (Sprint 2 G-04 still open) | High |  |  | Open | 18/10/2026
S3-08 | Price ranges not supported | RS-10 | Browse | 1. Check any ticket type | Range shown where a type has several prices | One price per type (Sprint 2 G-05 still open) | Medium |  |  | Open | 18/10/2026
S3-09 | 18 links go nowhere (Dashboard and Tickets pages) | LC-02, CA CS-15 | Dashboard | 1. Open /dashboard 2. Click Full standings, View full calendar, View all upgrades, any Upgrade or any event | Each opens its page | All link to "#" and nothing happens. New front end: the same upgrade and event links also appear on /tickets (8 more) | High |  |  | Open | 18/10/2026
S3-10 | Placeholder content on Dashboard ticket pass | CA CS-11 | Dashboard, Tickets | 1. Open /dashboard 2. Look at "Your tickets" | The user's real name, QR code and seat | "Your Name", "QR", "Row 1 · Seat 1" | Medium |  |  | Open | 18/10/2026
S3-11 | Race dates inconsistent across pages | CA CS-03 | Dashboard | 1. Open /dashboard and read the race dates 2. Compare with the home page and ticket days | Same race week dates everywhere | Dashboard says "1 – 2 January"; home says 4-day race week; tickets cover Thu-Sun | Medium |  |  | Open | 18/10/2026
S3-12 | Placeholder Settings page | CA CS-11 | Settings | 1. Open /settings | Real settings, or remove the link | "Settings will appear here." | Low |  |  | Open | 18/10/2026
S3-13 | Selection lost on refresh; Compare can't be linked | RS-27 | Browse, Compare | 1. Select 2 tickets 2. Refresh /tickets, or open /tickets/compare directly | Selection kept (or encoded in the URL) | Selection resets to 0 | Low |  |  | Open | 18/10/2026
S3-14 | Focus lost after removing a ticket on Compare | RS-31 | Compare | 1. Compare 3 tickets 2. Press Remove on one using the keyboard | Focus moves to the next ticket or heading | Focus drops to the page body | Low |  |  | Open | 18/10/2026
S3-15 | Subtitle text contrast below 4.5:1 | RS-52 | Browse | 1. Open /tickets 2. Check "Explore Australian Grand Prix ticket types..." in WebAIM | At least 4.5:1 | About 4.0:1 (grey on near-black) | Medium | Closed 18/10 on new front end: subtitle text now passes contrast |  | Closed | 18/10/2026
S3-16 | Limit-reached buttons' names don't match their text | RS-53 | Browse | 1. Select 3 tickets 2. Inspect a "Selection limit reached" button | Accessible name includes "Selection limit reached" | Name is only the ticket name (WCAG 2.5.3) | Low | Closed 18/10 on new front end: Compare checkboxes have matching labels |  | Closed | 18/10/2026
S3-17 | Colours don't match Grand Prix brand | CA CS-12 | All | 1. Open any page 2. Compare with the Grand Prix style guide | Grand Prix red, black and white | Green accents (Sprint 2 G-15 still open) | Medium | Closed 18/10 on new front end: red and black palette |  | Closed | 18/10/2026
S3-18 | Spinner instead of skeleton cards while loading | RS-35 | Browse | 1. Open /tickets in Chrome 2. DevTools > Network > Slow 3G 3. Reload (Cmd+Shift+R) | Skeleton placeholder per card, replaced by real cards | A single spinner until all tickets load (Sprint 2 G-07 still open) | Medium | See Screenshots tab; Closed 18/10 on new front end: skeleton cards show while loading |  | Closed | 18/10/2026
S3-19 | Circuit map shows a blank box while loading | RS-35 | Browse, Detail, Compare | 1. Same as S3-18 2. Watch the map area on each card as it appears | A sized placeholder (or skeleton) that clearly shows the map is loading | Blank white/grey box until the track image loads | Low | See Screenshots tab; Closed 18/10 on new front end: skeleton covers the map area while loading |  | Closed | 18/10/2026
S3-20 | Header shows "Welcome back, User" before the real name loads | RS-35 | All signed-in pages | 1. Throttle to 3G 2. Reload /tickets 3. Watch the header | Name appears once loaded, or no name until then | "Welcome back, User" shows first, then changes to the account name | Low | Closed 18/10 on new front end: no "Welcome back, User" header |  | Closed | 18/10/2026
S3-21 | Logo says "GARAGE" (template name) | CA CS-12 | All signed-in pages | 1. Sign in 2. Look at the sidebar or top-left logo | Grand Prix Ticketing name and logo | "GARAGE", from the garage-boilerplate template | Medium |  |  | Open | 18/10/2026
S3-22 | Compare checkbox is small | RS-21 (Detail) | Detail | 1. Open any ticket's details 2. Measure the Compare checkbox | At least 44px tap target (team standard, see S3W1 Q-03) | 24px checkbox | Low |  |  | Open | 18/10/2026
S3-23 | Dashboard has two different names | CA CS-08 | Navigation | 1. Compare the sidebar with the mobile bottom nav | Same label in both | Sidebar "Dashboard", bottom nav "Home" | Low |  |  | Open | 18/10/2026
S3-24 | Ticket names and buttons in all caps | CA CS-10 | Browse, Detail, Compare | 1. Open /tickets | Sentence or title case (CS-01, CS-10) | ALL CAPS ticket names, buttons and headings; harder to read | Low |  |  | Open | 18/10/2026
S3-25 | Ticket load failure shows an endless spinner | RS-43 to RS-46 | Browse | 1. Open /tickets in Chrome 2. DevTools > Network: right-click documents:runQuery > Block request domain 3. Reload (Cmd+Shift+R) | "We couldn't load tickets right now. Please try again." with a Retry button, shown within 10 seconds (S3W1 ERR-01 to ERR-03, FS-02) | Loading spinner forever; no message, no Retry, no timeout. Users can't tell anything is wrong | High | See Screenshots tab |  | Open | 18/10/2026
S3-26 | No pressed state on buttons | RS-12 | All | 1. Open /tickets on desktop 2. Click and hold "View details" | Button visibly changes while pressed | No change while held (Sprint 2 G-03 still open) | Low | Accepted as marginal by the BA, 18/10/2026 |  | Won't fix | 18/10/2026
S3-27 | Compare page shifts sideways on mobile | RS-33 | Compare | 1. Chrome device mode, 375px 2. Select 3 tickets, open Compare 3. Scroll left | Only the comparison area scrolls sideways; the page stays put | The whole page moves slightly sideways | Low | Accepted as marginal by the BA, 18/10/2026 |  | Won't fix | 18/10/2026
S3-28
S3-29
S3-30
S3-31
S3-32
S3-33
S3-34
S3-35
S3-36
S3-37
S3-38
S3-39
S3-40
S3-41
S3-42
S3-43
S3-44
S3-45
S3-46
S3-47
S3-48
S3-49
S3-50

## Screenshots
Evidence screenshots
S3-18 / S3-20: on 3G, /tickets shows only a spinner, and the header says "Welcome back, User" (18/10/2026)
S3-19: cards appear with blank white boxes where the circuit map should be, while albert-park-circuit.png is still loading (18/10/2026)
New front end on 3G (18/10/2026): skeleton cards (S3-18 closed), red palette (S3-17 closed), "GARAGE" logo (S3-21), "Your Name" / "Row 1 · Seat 1" placeholders (S3-10)
S3-25: firestore.googleapis.com blocked in DevTools; /tickets shows an endless spinner with no message or Retry (18/10/2026)